## Uncompleted 15-16
Electrical Engineering Department: Uncompleted action 2015\2016
Development and Follow-Up
Sr No. | The Document |  |  |  | Action | [6 empty] | Unit Coordinator's Comments | Follow Up |  |  | Remarks
| Title | Recommendation | Proposed by | Date | Activity | Responsibility | Period |  | KPI |  |  |  | Period |  | Responsibility
[7 empty] | From | To | KPI | Target | Actual |  | From | To
1 | Annual Report (NCAAA) (Academic Year 2014\2015) | 1- Specify for the same year to get indication Study the reasons and take action accordingly B.5,7 and 7 should be included and done 2- Study the course evaluation process and the teaching strategy of the faculty. 3- Include the summary 4- External Reviewing needed 5- Analyze the program evaluation outcome 6- provide program evaluation 7- Program Management and Administration should be in term of administration and management staff and facilities 8- KPIs should be specified and used 9- Benshmarks (internally and externally) should be determined | AEC | 2015-11-10 | 1) Annual report for academic year 2014/2015 should be discussed, revised and adjusted, All needed modifications should be tacken according to proposed recommandation, 2) Annual report for next academic year 2015/2016 should be developed and then compared to 2014/2015 Annual report in order to follow up all activities of EE department (making the progress rate in all activities of EE department), | QC | week 8 of SS | [5 empty] | 2016-02-01 | 2016-02-08 | FUC | 1) Anual report for academic year 2014/2015 was discussed and all needed modifications was tacken according to proposed recommandation. 2) Annual report completed and approved by EED
2 | Report: Senior Exit Interview-2015/2016 | Laboratories conditions: Some labs. such as EE205 don't include some components. | UCC | 2015-12-15 | 1) Check available components in the lab and therefore propose a list with needed components | LDC committee | 2nd week of SS | [5 empty] | W2/FS | W4/FS | FUC | 1) The Basic Circuits Lab subcommittee was formed and prepared a list with more urgent components, especially for EE212 & EE205 Labs, Requested components not yet received
3 | Report: Senior Exit Interview-2015/2017 | Students ask to open the labs in free time under the supervision of lab's technicians to practice the experiments and gain some practical skills. | UCC | 2015-12-15 | 2) HOD discussed this topic with instructors, All labs should opened to practice experiments and gain some practical skills under a student request approved by the HOD, | HOD | 2016-05-01 | [5 empty] | 2016-04-23 | 2016-05-01 | FUC | 2) HOD discussed this topic with faculty members, All labs should be open under a student request approved by the HOD
4 | Report: Senior Exit Interview-2015/2018 | The students also said there are several equipment they saw but they didn't take any experiment on it and they want to increase the number of experiments such as high voltage lab. | UCC | 2015-12-15 | 1) Collection of list of labs with co-requisite courses. 2) Prepare a report for all labs and courses including both following aspects: - Practical aspects: studying the lab equipment and experiments to be matched with the theorotical par. - Theorotical aspects: studying the lab description and comparing with course specification | Lab Development Committee (LDC) | 2016-05-01 | [5 empty] | 2016-04-23 | 2016-05-01 | FUC | 3) HOD request the LDC committee to check, for each lab, if all experiments described in the course description are covered. An action plan should be proposed by LDC committee and therefore approved by the HOD. | Completed
5 | Strategic Plan of Electrical Engineering Department-First semester 2015/2016 | 1) Evaluation of final exams of the first semester 2015/2016 | HOD | 2016-03-01 | Evaluate the final exams of the first semester 2015/2016 | AEC | 2016-03-10 | 2016-05-01 | [6 empty] | FUC | completed | In process
6 | Strategic Plan of Electrical Engineering Department-First semester 2015/2017 | 2) Evaluation of the first term course reports 2015/2016 | HOD | 2016-03-01 | Evaluate the first term course reports 2015/2016 | AEC (Dr, Quawasmi) | 2016-03-10 | 2016-05-01 | [6 empty] | FUC | completed | Passed Dead line
7 | Strategic Plan of Electrical Engineering Department-First semester 2015/2018 | 3) Evaluation of the course survey of the first semester 2015/2016 | HOD | 2016-03-01 | Evaluate the course survey of the first semester 2015/2016 | AEC | 2016-03-10 | 2016-04-15 | [6 empty] | FUC | completed
8 | Strategic Plan of Electrical Engineering Department-First semester 2015/2019 | 4) Evaluation of the student experience of the first semester 2015/2016 | HOD | 2016-03-01 | Evaluate the student experience of the first semester 2015/2016 | AEC | 2016-03-10 | 2016-04-15 | [6 empty] | FUC | completed
9 | Strategic Plan of Electrical Engineering Department-First semester 2015/2020 | 5) Evaluation and assessment of Course Scores Summary of the first semester 2015/2016 | HOD | 2016-03-01 | 1) Courses Score summary is evaluated. Improvements are noted compared to the previous year. 2) Prepare different assessmsent templates for further course evaluation | AEC | 2016-03-10 | 2016-04-15 | [6 empty] | FUC | completed
10 | Reprorts of LDC committee: Basic Circuits Lab Subcommittee report | Theoretical aspects: Studying the Lab descriptions and comparing with course specifications : 1) EE course description report don’t contain a description for EE 207 course. | LDC | 2016-01-31 | Theoretical aspects: Studying the Lab descriptions and comparing with course specifications : 1) Updating EE course description report by adding a full description of EE 207 course. | UPC | Fourth week of fall semester 16/17 | [5 empty] | W4/FS | W6/FS | FUC
11 | Reprorts of LDC committee: Basic Circuits Lab Subcommittee report | Practical aspects: Studying the Labs equipment and experiments to be match with the theoretical Part: 1) EE 207 Lab: Some equipment are missing like RS, T type, D type, JK and JK Master Slave Flip Flops, and Shift Register 2) EE 212: Some equipment are missing like BJT FET and MOS transistors 3) EE 205 Lab: Some equipment are missing like resistors, capacitors and inductors. | LDC | 2016-01-31 | Practical aspects: Studying the Labs equipment and experiments to be match with the theoretical Part: 1) Buying a new equipment to covers all EE 207 lab contents 2) Buying a new equipment to covers all EE 212 lab contents 3) Reequipped the Lab EE 205 with different equipment like resistors, capacitors and inductors. | LDC | Fourth week of fall semester 16/17 | [5 empty] | W4/FS | W6/FS | FUC | This action is considered on document N 8
12 | Reprorts of LDC committee: Communications Lab Subcommittee report | Theoretical aspects: Studying the Lab descriptions and comparing with course specifications : 1) EE 323 Lab: - The course description contains Analog and Digital communications Experiments - The course description contains Optical fiber experiments - Course description and course specifications are different 2) EE 427 Lab: - Course specifications and Course descriptions are different - Course specifications contains only Digital Signal Processing experiments | LDC | 2016-01-31 | Theoretical aspects: Studying the Lab descriptions and comparing with course specifications : 1) EE 323 Lab: - Change the contents of the course description to be as in the course specifications - Remove Optical fiber experiments because no related previous theory about fiber communications. 2) EE 427 Lab: - Change course specifications to be as course description | UPC | Fourth week of fall semester 16/17 | [5 empty] | W4/FS | W6/FS | FUC
13 | Reprorts of LDC committee: PowerLab Subcommittee report | Theoretical aspects: Studying the Lab descriptions and comparing with course specifications : 1) EE 271 Lab: - Some part of course description is missing in course specifications. - Course specifications contains only Principle of Electrical Machines (EE 288) course experiments. 2) EE 479 Lab: Lab name is protection and high voltage Lab but course description does not contain any experiments related to High Voltage . | LDC | 2016-01-31 | Theoretical aspects: Studying the Lab descriptions and comparing with course specifications : 1) EE 271 Lab: - Experiments related to short transmission lines for Fundamentals of electrical power systems (EE270) should be added in course specifications - Course specifications are required to be amended according to course description 2) EE 479 Lab: Course description and specifications are not up to the mark. | UPC | Fourth week of fall semester 16/17 | [5 empty] | W4/FS | W6/FS | FUC
14 | Reprorts of LDC committee: PowerLab Subcommittee report | Practical aspects: Studying the Labs equipment and experiments to be match with the theoretical Part: 1) EE 479 Lab: There is no equipment for High Voltage Engineering Systems (EE 477) Experiments | LDC | 2016-01-31 | Practical aspects: Studying the Labs equipment and experiments to be match with the theoretical Part: 1) EE 479 Lab: A new separate fully equipped lab is required to perform High Voltage Engineering Systems (EE 477) course experiments | LDC | Fourth week of fall semester 16/17 | [5 empty] | W4/FS | W6/FS | FUC

## Operational Plan 16-17
Electrical Engineering Department: Operational Plan for 2016/2017
Development and Follow-Up
Sr No. | The Document |  |  |  | Action | [6 empty] | Unit Coordinator's Comments | Follow Up |  |  | Remarks
| Title | Recommendation | Proposed by | Date | Activity | Responsibility | Period |  | KPI |  |  |  | Period |  | Responsibility
[7 empty] | From | To | KPI | Target | Actual |  | From | To
1 | Operational plans of EE Department Committees 2016\2017: AAC | Complete the accreditation process by ABET | AAC | 2016-09-26 | Completing writing Draft ABET SSR | AAC | W2/FS | W3/FS |  |  |  | Complete ABET SSR (Draft) | W3/FS | W5/FS | FUC | in progress
2 | Operational plans of EE Department Committees 2016\2017: AAC | Complete the accreditation process by ABET | AAC | 2016-09-26 | Completing Final ABET SSR | AAC | W3/FS | W6/FS |  |  |  | Complete ABET SSR (Final Version) | W5/FS | W7/FS | FUC | in progress | Completed
3 | Operational plans of EE Department Committees 2016\2017: AAC | Performance Indicators measurement and benchmarking for Academic Program | AAC | 2016-09-26 | Determining the EE KPIs and benchmarking | AAC | W11/FS | W11/FS |  |  |  | To discuss with QC, the KPIs and how to determine the benchmark. | W11/FS | W13/FS | FUC |  | In process
4 | Operational plans of EE Department Committees 2016\2017: AAC | Improvement of administrative and quality work in the department | AAC | 2016-09-26 | Organizing a workshop “EE ABET accreditation: ABET SSR” | AAC | W14/FS | W15/FS |  |  |  | To discuss the ABET SSR contents | W11/FS | W13/FS | FUC |  | Passed Dead line
5 | Operational plans of EE Department Committees 2016\2017: AAC | Improvement of administrative and quality work in the department | AAC | 2016-09-26 | Organizing a workshop “EE ABET accreditation: How to meet ABET reviewing Committee | AAC | W6/SS | W7/SS |  |  |  | To discuss the preparation of faculty members to meet ABET requirements. | W7/FS | W9/FS | FUC
6 | Operational plans of EE Department Committees 2016\2017: AAC | Periodic evaluation of academic program | AAC | 2016-09-26 | Internal Reviewing of EE program | AAC | W10/SS | W12/SS |  |  |  | To evaluate at least 50% of courses | W11/FS | W13/FS | FUC
7 | Operational plans of EE Department Committees 2016\2017: AAC | Activation of the independent evaluation of the academic program | AAC | 2016-09-26 | Evaluate EE program by independent committee | AAC | W12/SS | W14/SS |  |  |  | To a have a full an independent evaluation report. | W13/FS | W15/FS | FUC
8 | Operational plans of EE Department Committees 2016\2017: AAC | Activation of Advisory board of E program | AAC | 2016-09-26 | Performing meetings with the advisory boards of the EE program | AAC | W11/FS | W12/FS |  |  |  | To discuss ABET SSR with the advisory board | W11/FS | W13/FS | FUC
9 | Operational plans of EE Department Committees 2016\2017: AAC | Activation of Advisory board of E program | AAC | 2016-09-26 | Performing meetings with the advisory boards of the EE program | AAC | W11/SS | W11/SS |  |  |  | To discuss ABET SSR with the advisory board | W11/FS | W12/FS | FUC
10 | Operational plans of EE Department Committees 2016\2017: AEC | Improving the quality work in the department | AEC | 2016-09-26 | Assessment and evaluation of all reports and surveys provided by units and committees | AEC | W1/FS | W16/SS |  |  |  | During the academic year. | W5/FS | W2/SS | FUC | In progress
11 | Operational plans of EE Department Committees 2016\2017: AEC | Improving the quality work in the department | AEC | 42639 | Analyzing Annual Program Report | AEC | W0/FS | W4/FS |  |  |  | For the 2015/2016 Year | W1/FS | W5/FS | FUC | In progress
12 | Operational plans of EE Department Committees 2016\2017: AEC | Improving the quality work in the department | AEC | 2016-09-26 | Analyzing Program Surveys (Course, program and experience) | AEC | W0/FS | W4/FS |  |  |  | For the second semester 2015\2016. Raw data will be requested from college | W1/FS | W5/FS | FUC | Completed
13 | Operational plans of EE Department Committees 2016\2017: AEC | Improving the quality work in the department | AEC | 2016-09-26 | Analyzing Program Surveys (Course, program and experience) | AEC | W0/SS | W1/SS |  |  |  | For the First semester 2016\2017, Raw data will be requested from college | W1/SS | W2/SS | FUC
14 | Operational plans of EE Department Committees 2016\2017: AEC | Improving the quality work in the department | AEC | 2016-09-26 | Analyzing the Experience Field Report | AEC | During the academic year 16/17 |  |  |  |  | For the 2015/2016 Year | W5/FS | W17/SS | FUC | in progress
15 | Operational plans of EE Department Committees 2016\2017: AEC | Enhancing the quality of exams | AEC | 2016-09-26 | Evaluation of Final exams | AEC | W0/FS | W4/FS |  |  |  | Evaluation of Second semester final exams (2015\2016) | W1/FS | W5/FS | FUC | Completed
16 | Operational plans of EE Department Committees 2016\2017: AEC | Enhancing the quality of exams | AEC | 2016-09-26 | Evaluation of Final exams | AEC | W0/SS | W1/SS |  |  |  | Evaluation of First semester final exams (2016\2017) | W1/SS | W2/SS | FUC
17 | Operational plans of EE Department Committees 2016\2017: AEC | Enhancing the quality of exams | AEC | 2016-09-26 | A workshop: “How to choose the suitable assessment method based on the course contents” | AEC | W6/SS | W7/SS |  |  |  | The title can be discussed with strategic and planning committee | W7/SS | W8/SS | FUC
18 | Operational plans of EE Department Committees 2016\2017: AEC | Development of faculty members' skills in the areas of assessment and evaluation | AEC | 2016-09-26 | A workshop “assessment and evaluation skills” | AEC | W11/SS | W12/SS |  |  |  | The title can be discussed with the strategic committee | W12/SS | W13/SS | FUC
19 | Operational plans of EE Department Committees 2016\2017: DSC | Making reaching of regulations and guidelines more available and flexible for students and faculty members | DSC | 2016-09-26 | Inform faculty members about regulations and guidelines | DSC | W1 /FS | W2/ FS |  |  |  | New regulations and guidelines to be sent to faculty members by E-mail | W1/FS | W3/ FS | FUC | Completed: No new staff members
20 | Operational plans of EE Department Committees 2016\2017: DSC | Making reaching of regulations and guidelines more available and flexible for students and faculty members | DSC | 2016-09-26 | Inform faculty members about regulations and guidelines | DSC | W1 /SS | W2/ SS |  |  |  | New regulations and guidelines to be sent to faculty members by E-mail | W1/SS | W3/ SS
21 | Operational plans of EE Department Committees 2016\2017: DSC | Making reaching of regulations and guidelines more available and flexible for students and faculty members | DSC | 2016-09-27 | Inform new students about regulations and guidelines: S1 | DSC | W1/FS | W1/FS |  |  |  | * A booklet of regulation for each new student. * A hard copy “one page” of most important regulations for all EE students | W2/FS | W2/FS | FUC | Completed: a Boklet is prepared
22 | Operational plans of EE Department Committees 2016\2017: DSC | Making reaching of regulations and guidelines more available and flexible for students and faculty members | DSC | 2016-09-28 | Inform new students about regulations and guidelines: S2 | DSC | W1 SS | W1 SS |  |  |  | * A booklet of regulation for each new student. * A hard copy “one page” of most important regulations for all EE students | W2/SS | W2SS | FUC
23 | Operational plans of EE Department Committees 2016\2017: DSC | Follow-up the affairs of the college’s alumni and communicate with them to develop of academic programs | DSC | 2016-09-29 | Collecting addresses of work and make a communication with graduates | DSC | W1/FS | W1 /SS |  |  |  | Communicate with 60% of graduates for the 2015\2016 academic year | W1/FS | W1 /SS | FUC | In progress: Some graduates email adresses has been collected
24 | Operational plans of EE Department Committees 2016\2017: DSC | Follow-up the affairs of the college’s alumni and communicate with them to develop of academic programs | DSC | 2016-09-30 | To prepare a report about Alumni feedback and development suggestion | DSC | [5 empty] | In this report: 1- responses to different surveys 2-addresses and contacts of information of graduated students 3- difficulties and proposed solutions faced during the process. | W1/SS | W1/SS | FUC
25 | Operational plans of EE Department Committees 2016\2017: DSC | Enhancing the flexibility of work in EE departments | DSC | 2016-10-01 | Supporting EE activities | DSC | W1FS | W6FS |  |  |  | Two projects or activities to serve the community | W2/FS | W7/SS | FUC | In progress
26 | Operational plans of EE Department Committees 2016\2017: DSC | Enhancing the flexibility of work in EE departments | DSC | 2016-10-02 | Preparing the EE annual report | DSC | W15/SS | W16/SS |  |  |  |  | W16/SS | W17/SS | FUC
27 | Operational plans of EE Department Committees 2016\2017: DAC | Activating authentication system | DAC | 2016-09-26 | Identification of EE data needed | DAC | W1/FS | W3/FS |  |  |  | All EE data (Students, faculty, documents, specifications, reports,) should be determined as a list based on the feedback from the HOD, units and committees. The list can be updated during the academic year. | W2/FS | W4/FS | FUC | completed
28 | Operational plans of EE Department Committees 2016\2017: DAC | Activating authentication system | DAC | 2016-09-26 | Data Collection | DAC | W1/FS | W16/SS |  |  |  | Collection of data should be systematic and some data should be approved before they will be documented and archived. Source of data should be mention for every document. | W2/FS | W17/SS | FUC | in progress
29 | Operational plans of EE Department Committees 2016\2017: DAC | Activating authentication system | DAC | 2016-09-26 | Data processing and preparation with statistical analysis | DAC | W1/FS | W16/SS |  |  |  | Data based on surveys should be prepared with statistical analysis | W2/FS | W17/SS | FUC | in progress
30 | Operational plans of EE Department Committees 2016\2017: DAC | Activating authentication system | DAC | 2016-09-26 | Archiving and database management | DAC | W1/FS | W16/SS |  |  |  | All EE data and documents should be archived in such way so it can be easy to be found extracted and used. | W2/FS | W17/SS | FUC | in progress
31 | Operational plans of EE Department Committees 2016\2017: DAC | Activating authentication system | DAC | 2016-09-26 | Unifying documents and forms in the department | DAC | W1/FS | W16/SS |  |  |  | For documents that are used at college level and by EE department, the unifying and last versions should be checked. | W2/FS | W17/SS | FUC | in progress
32 | Operational plans of EE Department Committees 2016\2017: DAC | Activating authentication system | DAC | 2016-09-26 | Recording all activities in the department | DAC | W1/FS | W16/SS |  |  |  | Periodically collecting and recording information about EE activities by sending E-mail to all units and committees to provide you with the data after finishing the activity. | W2/FS | W17/SS | FUC | in progress
33 | Operational plans of EE Department Committees 2016\2017: EPC | Enhancing student’ skills through training, Labs and workshops. | EPC | 2016-09-26 | A workshop “Engineering Practice importance and Regulations” | EPC | W3/SS | W3/SS |  |  |  | The target is all students. Providing the HOD with a full report about activity. | W4/SS | W4/SS | FUC
34 | Operational plans of EE Department Committees 2016\2017: EPC | Providing training opportunities for students | EPC | 2016-09-26 | Providing students with regulations, forms and training opportunities | EPC | W6/SS | W10/SS |  |  |  |  | W7/SS | W11/SS | FUC
35 | Operational plans of EE Department Committees 2016\2017: EPC | Providing training opportunities for students | EPC | 2016-09-26 | Organizing a meeting with students to discuss the training summer regulations | EPC | W10/SS | W11/SS |  |  |  | Informing the HOD about the time and date | W7/SS | W11/SS | FUC
36 | Operational plans of EE Department Committees 2016\2017: EPC | Development of summer training skills | EPC | 2016-09-26 | Following-up the training process in summer | EPC | W15/SS | W16/SS |  |  |  | Putting a plan to follow-up training process of EE students | W16/SS | W17/SS | FUC
37 | Operational plans of EE Department Committees 2016\2017: EPC | Development of summer training skills | EPC | 2016-09-26 | Make a survey for s students satisfactions about training summer | EPC | W5/FS | W6/SS |  |  |  |  | W6/SS | W7/SS | FUC | IN PROGRESS
38 | Operational plans of EE Department Committees 2016\2017: LDC | Enhancing the performance of Technicians regarding lab’s courses | LDC | 2016-09-26 | Participating of technician in special programs to enhance their practical performance | LDC | W1/SS | W2/SS |  |  |  |  | W2/SS | W3/SS | FUC
39 | Operational plans of EE Department Committees 2016\2017: LDC | Enhancing the performance of Technicians regarding lab’s courses | LDC | 2016-09-27 | Creating a procedure to organize work of technicians and to define their main responsibilities | LDC | W1/FS | W2/FS |  |  |  |  | W2/FS | W3/FS | FUC | Completed: No technician available
40 | Operational plans of EE Department Committees 2016\2017: LDC | Enhancing the performance of Technicians regarding lab’s courses | LDC | 2016-09-28 | Organizing a presentation “Development of EE Labs | LDC | W6/FS | W6/SS |  |  |  |  | W6/FS | W7/SS | FUC
41 | Operational plans of EE Department Committees 2016\2017: LDC | Meeting safety and occupational environment of Labs | LDC | 2016-09-29 | Lab conditions in EE from the OHSAS 18001 point of view | LDC | W2/FS | W4/FS |  |  |  |  | W3/FS | W5/FS | FUC | Completed: OEH will perform this task
42 | Operational plans of EE Department Committees 2016\2017: QC | Educational sessions about Quality in Education | QC | 2016-09-26 | Preparing a brochure or short handbook including main quality information needed for faculty members | QC | W8/FS | W9/FS |  |  |  |  | W9/FS | W10/FS | FUC
43 | Operational plans of EE Department Committees 2016\2017: QC | Educational sessions about Quality in Education | QC | 2016-09-26 | Organizing A lecture “Why we need to be accredited?” | QC | W8/SS | W9/SS |  |  |  |  | W9/SS | W10/SS | FUC
44 | Operational plans of EE Department Committees 2016\2017: QC | Educational sessions about Quality in Education | QC | 2016-09-26 | Request to publish the rules and regulation on the EE website | QC | W3/FS | W5/FS |  |  |  |  | W4/FS | W6/FS | FUC | Completed: An email was sent to the HOD
45 | Operational plans of EE Department Committees 2016\2017: QC | Analyzing the internal feedback from Quality Deanship (internal reviewing process) and suggest an action plan | QC | 2016-09-26 | Organizing special meetings to analyze the internal feedback and writing a report and suggest action plan | QC | W10/FS | W11/FS |  |  |  |  | W11/FS | W12/FS | FUC
46 | Operational plans of EE Department Committees 2016\2017: QC | Analyzing the internal feedback from Quality Deanship (internal reviewing process) and suggest an action plan | QC | 2016-09-26 | Making biannual meeting with committee’s coordinators to share information and determining quality work and needs of QC | QC | W12/FS | W13/FS |  |  |  |  | W13/FS | W14/FS | FUC
47 | Operational plans of EE Department Committees 2016\2017: QC | Analyzing the internal feedback from Quality Deanship (internal reviewing process) and suggest an action plan | QC | 2016-09-26 | Making biannual meeting with committee’s coordinators to share information and determining quality work and needs of QC | QC | W12/SS | W13/SS |  |  |  |  | W13/SS | W14/SS | FUC
48 | Operational plans of EE Department Committees 2016\2017: QC | Periodic evaluation of Quality system run the program | QC | 2016-09-26 | Preparing a report regarding satisfaction level of beneficiaries | QC | W6/FS | W8/FS |  |  |  |  | W7/FS | W9/FS | FUC
49 | Operational plans of EE Department Committees 2016\2017: QC | Periodic evaluation of Quality system run the program | QC | 2016-09-26 | Internally evaluation of EE program | QC | W6/SS | W9/SS |  |  |  |  | W7/SS | W10/SS | FUC
50 | Operational plans of EE Department Committees 2016\2017: QC | Quality assurance of courses File | QC | 2016-09-26 | Follow-up Course portfolio first semester | QC | W0/FS | W3/FS |  |  |  |  | W3/FS | W5/FS | FUC | In progress
51 | Operational plans of EE Department Committees 2016\2017: QC | Quality assurance of courses File | QC | 2016-09-26 | Follow-up Course portfolio second semester | QC | W1/SS | W3/SS |  |  |  |  | W2/SS | W4/SS | FUC
52 | Operational plans of EE Department Committees 2016\2017: QC | Quality Assurance of learning outcomes for the academic program | QC | 2016-09-26 | To follow the indirect and direct assessment of CLOs | QC | W1/FS | W16/FS |  |  |  |  | W2/FS | W2/SS | FUC
53 | Operational plans of EE Department Committees 2016\2017: QC | Quality Assurance of learning outcomes for the academic program | QC | 2016-09-26 | To follow the indirect and direct assessment of CLOs | QC | W1/SS | W16/SS |  |  |  |  | W2/FS | W2/SS | FUC
54 | Operational plans of EE Department Committees 2016\2017: QC | Quality Assurance of the reports and specifications of program and courses | QC | 2016-09-26 | Checking and evaluation of course specifications and reports of the program | QC | W1/FS | W16/SS |  |  |  |  | W2/FS | W2/SS | FUC
55 | Operational plans of EE Department Committees 2016\2017: URAC | Enhancing student’ skills through training, Labs and workshops. | UR AC | 2016-09-26 | Establishing EE club or (incubator) or an innovation group to support students to start their own projects. | UR AC | W3/SS | W5/SS |  |  |  |  | W4/SS | W6/SS | FUC
56 | Operational plans of EE Department Committees 2016\2017: URAC | Enhancing student’ skills through training, Labs and workshops. | UR AC | 2016-09-27 | Support participations of students in conferences Mainly (The seventh students conference organized by MOHE) | UR AC | W3/FS | W4/FS |  |  |  |  | W4/FS | W5/FS | FUC | completed
57 | Operational plans of EE Department Committees 2016\2017: URAC | Enhancing student’ skills through training, Labs and workshops. | UR AC | 2016-09-28 | Announce a competition for best Micro-project | UR AC | W5/FS | W6/FS |  |  |  |  | W6/FS | W7/FS | FUC
58 | Operational plans of EE Department Committees 2016\2017: URAC | Educate students about the importance of research | UR AC | 2016-09-29 | Organizing a meeting with students and show explain them the importance of research in their life | UR AC | W8/SS | W9/SS |  |  |  |  | W9/SS | W10/SS | FUC
59 | Operational plans of EE Department Committees 2016\2017: URAC | Educate students about the importance of research | UR AC | 2016-09-30 | Following the students research progress in the departments | UR AC | W12/SS | W13/SS |  |  |  |  | W13/SS | W14/SS | FUC
60 | Operational plans of EE Department Committees 2016\2017: URAC | Implementation of programs for entrepreneurship and student innovation projects | UR AC | 2016-10-01 | Writing a program for entrepreneurship and student innovation projects | UR AC | W7/FS | W8/FS |  |  |  |  | W8/FS | W8/SS | FUC
61 | Operational plans of EE Department Committees 2016\2017: UCSC | Improving the Educational process to support the high ethical and professional standards | UC SC | 2016-09-26 | A workshop “The importance of Engineering Ethics for your students “ | UC SC | W7/SS | W8/SS |  |  |  |  | W8/SS | W9/SS | FUC
62 | Operational plans of EE Department Committees 2016\2017: UCSC | Improving the Educational process to support the high ethical and professional standards | UC SC | 2016-09-26 | Induction Day for the new students | UC SC | W2/FS | W4/FS |  |  |  |  | W3/FS | W5/FS | FUC | Completed: introduction day was organized on 11/11/2016
63 | Operational plans of EE Department Committees 2016\2017: UCSC | Improving the Educational process to support the high ethical and professional standards | UC SC | 2016-09-26 | Induction Day for the new students | UC SC | W2/SS | W4/SS |  |  |  |  | W3/SS | W5/SS | FUC
64 | Operational plans of EE Department Committees 2016\2017: UCSC | Program to support unsurpassed students | UC SC | 2016-09-26 | Collecting data from instructors about unsurpassed students for support and solving their problems | UC SC | W10/FS | W10/FS |  |  |  |  | W10/FS | W11/FS | FUC
65 | Operational plans of EE Department Committees 2016\2017: UCSC | Organizing lectures, scientific visiting’s and workshop for students to enhance their skills and to improve their academic levels. | UC SC | 2016-09-26 | Jalajil substation visit | UC SC | W4/FS | W5/FS |  |  |  |  | W5/FS | W6/FS | FUC | IN PROGRESS
66 | Operational plans of EE Department Committees 2016\2017: UCSC | Organizing lectures, scientific visiting’s and workshop for students to enhance their skills and to improve their academic levels. | UC SC | 2016-09-26 | STC Visit | UC SC | W11/FS | W12/FS |  |  |  |  | W12/FS | W13/FS | FUC
67 | Operational plans of EE Department Committees 2016\2017: UCSC | Organizing lectures, scientific visiting’s and workshop for students to enhance their skills and to improve their academic levels. | UC SC | 2016-09-26 | Workshop about “A preparation for Interviews and writing a CV” | UC SC | W11/SS | W12/SS |  |  |  |  | W12/SS | W13/SS | FUC
68 | Operational plans of EE Department Committees 2016\2017: UCSC | Organizing lectures, scientific visiting’s and workshop for students to enhance their skills and to improve their academic levels. | UC SC | 2016-09-26 | Meeting with all EE students | UC SC | W10/FS | W10/SS |  |  |  |  | W10/FS | W11/FS | FUC
69 | Operational plans of EE Department Committees 2016\2017: UCSC | Improve academic Advising | UC SC | 2016-09-26 | Workshop on Academic Advising “The importance of Academic Advising” | UC SC | W4/FS | W5/FS |  |  |  |  | W5/FS | W6/FS | FUC | IN PROGRESS
70 | Operational plans of EE Department Committees 2016\2017: UCSC | Improve academic Advising | UC SC | 42639 | Supervising and following up the academic advising process in the first week | UC SC | W1/FS | W1/SS |  |  |  |  | W1/FS | W3/FS | FUC | Completed
71 | Operational plans of EE Department Committees 2016\2017: UCSC | Improve academic Advising | UC SC | 42639 | Preparing advising brochures and announcement s for students, Inform students about regulations and guidelines and Proposing a template and appealing procedure | UC SC | W1/FS | W1/SS |  |  |  |  | W1/FS | W3/FS | FUC | Completed: No budget to prepare brochure
72 | Operational plans of EE Department Committees 2016\2017: UCSC | Expand the acceptance opportunities in undergraduate EE program | UC SC | 2016-09-26 | Organize an orientation day about the program and tracks. | UC SC | W5/ FS | W5 /SS |  |  |  |  | W6/FS | W6/SS | FUC
73 | Operational plans of EE Department Committees 2016\2017: UCSC | Development of admission standards of students | UC SC | 2016-09-26 | Suggestion of new admission standards to be discussed at college level | UC SC | W3/SS | W4/SS |  |  |  |  | W4/SS | W5/SS | FUC
74 | Operational plans of EE Department Committees 2016\2017: UCSC | Organizing of a student award in volunteer work | UC SC | 2016-09-26 | Writing a proposal about student award in volunteer work | UC SC | W9/FS | W10/FS |  |  |  |  | W10/FS | W11/FS | FUC
75 | Operational plans of EE Department Committees 2016\2017:UPC | Improving the EE program to meet high standards | UPC | 2016-09-26 | Analyzing Course Reports and writing action plan | UPC | W1/SS | W2/SS |  |  |  |  | W2/SS | W3/SS | FUC
76 | Operational plans of EE Department Committees 2016\2017:UPC | Improving the overall satisfaction rate of students for courses | UPC | 2016-09-26 | Improving the EE curriculum based on the UPC operational plan | UPC | W2/FS | W15/SS |  |  |  |  | W3/FS | W16/SS | FUC | IN PROGRESS
77 | Operational plans of EE Department Committees 2016\2017:UPC | Development of study plans | UPC | 2016-09-26 | Improving the EE curriculum based on the UPC operational plan | UPC | W2/FS | W15/SS |  |  |  |  | W3/FS | W16/SS | FUC | IN PROGRESS
78 | Operational plans of EE Department Committees 2016\2017:UPC | Developing academic programs regarding sustainable development issues | UPC | 2016-09-26 | Considering the sustainable development issues in the development of EE curriculum. | UPC | W12/SS | W13/SS |  |  |  |  | W13/SS | W14/SS | FUC
79 | Operational plans of EE Department Committees 2016\2017: WAC | Improving the EE website | WAC | 2016-09-26 | Checking all links, pages and contents of the EE webpage | WAC | W3/FS | W4/FS |  |  |  |  | W4/FS | W5/FS | FUC | Completed
80 | Operational plans of EE Department Committees 2016\2017: WAC | Improving the EE website | WAC | 2016-09-26 | Discussing the report actions and recommendations, needed information and material that should be updated with strategic committee. | WAC | W4/FS | W4/FS |  |  |  |  | W5/FS | W6/FS | FUC | In progress
81 | Operational plans of EE Department Committees 2016\2017: WAC | Improving the EE website | WAC | 2016-09-26 | Updating the EE website: Regulations, accreditation information, Faculty, board of advisors, EE program documents (Specifications, curriculum, reports). | WAC | W5/FS | W6/FS |  |  |  |  | W6/FS | W7/FS | FUC | In progress
82 | Operational plans of EE Department Committees 2016\2017: WAC | Improving the EE website | WAC | 2016-09-26 | All Courses (descriptions, specifications) Arabic (Links from Arabic webpage) and English should be in the EE website. | WAC | W5/FS | W6/FS |  |  |  |  | W6/FS | W7/FS | FUC | In progress
83 | Operational plans of EE Department Committees 2016\2017: BP | * Continue the Bridging Program with the required standard. * Investigate what EE program can provide for the community | BP | 2016-09-26 | Investigate projects that support community | BP | W1/FS | W6/SS |  |  |  |  | W2/FS | W7/SS | FUC | IN PROGRESS
84 | Operational plans of EE Department Committees 2016\2017: BP | * Continue the Bridging Program with the required standard. * Investigate what EE program can provide for the community | BP | 2016-09-26 | Modification of regulation equivalency of courses | BP | W12/SS | W13/SS |  |  |  |  | W13/SS | W14/SS | FUC
85 | Operational plans of EE Department Committees 2016\2017: BP | * Continue the Bridging Program with the required standard. * Investigate what EE program can provide for the community | BP | 2016-09-26 | Making a meeting with new students | BP | W1/FS | W3/FS |  |  |  |  | W2/FS | W4/FS | FUC | COMPLETED
86 | Operational plans of EE Department Committees 2016\2017: FUC | Follow up with department activities | FUC | 2016-09-26 | follow-up the EE operational plan | FUC | W1/FS | W17/SS |  |  |  |  | W2/FS | W7/SS | FUC | IN PROGRESS
87 | Operational plans of EE Department Committees 2016\2017: FUC | Follow up with department activities | FUC | 2016-09-26 | follow-up other activities to the operational during the academic year | FUC | W1/FS | W17/SS |  |  |  |  | W2/FS | W7/SS | FUC | IN PROGRESS
88 | Operational plans of EE Department Committees 2016\2017: GPC | Establishing Master Degree Program in Electrical Engineering | GPC | 2016-09-26 | A presentation: “Master Degree in EE: Importance and capabilities” | GPC | W5/SS | W6/SS |  |  |  | a workshop to discuss the importance the master degree and to a have a feedback about types and regulations | W6/SS | W7/SS | FUC
89 | Operational plans of EE Department Committees 2016\2017: GPC | Establishing Master Degree Program in Electrical Engineering | GPC | 2016-09-26 | Proposing a graduate program: Draft | GPC | W8/SS | W9/SS |  |  |  | To propose the first draft of Master Degree Program | W9/SS | W10/SS | FUC
90 | Operational plans of EE Department Committees 2016\2017: GPC | Establishing Master Degree Program in Electrical Engineering | GPC | 2016-09-26 | Proposing a graduate program: Final Proposal | GPC | W11/SS | W12/SS |  |  |  | To propose the final proposal of Master Degree Program to be approved by EE council | W12/SS | W13/SS | FUC
91 | Operational plans of EE Department Committees 2016\2017: IC | Increase number of Associate Prof and Professor. | IC | 2016-09-26 | Studying more applicants ‘documentation | IC | W1/FS | W15/SS |  |  |  | This is for postgraduate’s studies in the EE program | W3/FS | W17/SS | FUC
92 | Operational plans of EE Department Committees 2016\2017: IC | Improving the appropriate of faculty member’s disciplines with courses and administrative work | IC | 2016-09-26 | Preparing an analysis report about the faculty member’s disciplines with courses and administrative work | IC | W1 SS | W14SS |  |  |  | The report for improving process. | W3/FS | W17/SS | FUC | IN PROGRESS
93 | Operational plans of EE Department Committees 2016\2017: IC | Improving the academic job rates of Saudi citizens | IC | 2016-09-26 | Studying more applicants ‘documentation of Saudi citizens | IC | W9/FS | W10/FS |  |  |  | Requesting all Saudi applicant’s documents (If applicable) | W10/FS | W11/SS | FUC
94 | Operational plans of EE Department Committees 2016\2017: RCSC | Establish Research Center. | R&CSC | 2016-09-26 | Preparing proposal | RCSC | W1/FS | W14/FS |  |  |  | Proposing a report including the requirements for establishing a search center. | W1/FS | W16/FS | FUC
95 | Operational plans of EE Department Committees 2016\2017: RCSC | Organizing workshops about research methodology and how to write research papers | R&CSC | 2016-09-26 | Organizing workshop “How to write a good paper”. | RCSC | W8/ FS | W9/FS |  |  |  | The title is subject for discussion with the strategic committee | W9/FS | W10/FS | FUC
96 | Operational plans of EE Department Committees 2016\2017: RCSC | Organizing workshops and lectures about research national and international funded projects | R&CSC | 2016-09-26 | Organizing a workshop “Important steps to be funded” | RCSC | W8/ SS | W9/SS |  |  |  | The title is subject for discussion with the strategic committee | W9/SS | W10/SS | FUC
97 | Operational plans of EE Department Committees 2016\2017: RCSC | Encouraging researchers to work with research that helps to improve the environment and society | R&CSC | 2016-09-26 | Organizing a visit to industrial or social place to be familiar with their needs | RCSC | W11/FS | W12/FS |  |  |  | Writing a report about visit and provide instructors with society needs. | W12/FS | W13/FS | FUC
98 | Operational plans of EE Department Committees 2016\2017: RCSC | Organizing conferences and scientific days | R&CSC | 2016-09-26 | Preparing a proposal for organizing a scientific day | RCSC | W5/SS | W6/SS |  |  |  | The proposal should contain information about the day, time and date and material needs. | W6/FS | W7/SS | FUC
99 | Operational plans of EE Department Committees 2016\2017: RCSC | Restructuring some disciplines according to the needs of local and national community | R&CSC | 2016-09-26 | Proposal “Courses for local and national community” | RCSC | W5/FS | W7/SS |  |  |  | Cooperating with UPC to make some contents of EE course to cover partially local and national needs. | W6/FS | W7/SS | FUC
100 | Operational plans of EE Department Committees 2016\2017: RCSC | Development of a program to improve the scientific productivity | R&CSC | 2016-09-26 | Proposing a program that will help in increasing the number research papers and publications. | RCSC | W1/SS | W2/SS |  |  |  | The program should conation statistical analysis about previous published papers under Majmaah university, comparing results with benchmark and a recommendation and action plan for increasing the published papers: instructor ratio. | W2/SS | W3/SS | FUC
101 | Operational plans of EE Department Committees 2016\2017: RCSC | Developing the awareness of students and faculty members to intellectual property rights and registration procedures | R&CSC | 2016-09-26 | Preparing and publishing rights and registration procedures for faculty members and students | RCSC | W12/SS | W13/SS |  |  |  | The ethical concepts, plagiarism should be included in the rights and registration procedure. | W13/SS | W14/SS | FUC
102 | Operational plans of EE Department Committees 2016\2017: RCSC | Support and motivate Multi-disciplinary research projects | R&CSC | 2016-09-26 | Encouraging faculty members to work multidisciplinary with other programs by support them through cooperation with other research committees in the other programs | RCSC | W7/FS | W7/FS |  |  |  | In this case, the committee should contact the research vice-deanship to get information about cooperation | W7/FS | W8/FS | FUC
103 | Operational plans of EE Department Committees 2016\2017: RCSC | Motivate of faculty members to participate and submit funded scientific research by the University, the Kingdom and international | R&CSC | 2016-09-26 | Periodically providing instructors with funded universities, centers and organizations and encourage them to participate. | RCSC | W1/FS | W16/SS |  |  |  |  | W2/FS | W16/SS | FUC
104 | Operational plans of EE Department Committees 2016\2017: RCSC | Providing engineering and technical consulting | R&CSC | 2016-09-26 | Providing consulting and training course for society | RCSC | W1/FS | W16/SS |  |  |  | Preparing a booklet with the training courses that can instructors or consultation services. The booklet can be written base on the instructors’ skills, Labs readiness. | W2/FS | W16/SS | FUC
105 | Operational plans of EE Department Committees 2016\2017: SPC | Prepare Scheduling Program and major Exams | SPC | 2016-09-26 | Planning Course Scheduling | SPC | W1/FS | W2/FS |  |  |  |  | W2/FS | W3/FS | FUC | COMPLETED
106 | Operational plans of EE Department Committees 2016\2017: SPC | Prepare Scheduling Program and major Exams | SPC | 2016-09-26 | Planning Course Scheduling | SPC | W1/SS | W2/SS |  |  |  |  | W2/SS | W3/SS | FUC
107 | Operational plans of EE Department Committees 2016\2017: SPC | Prepare Scheduling Program and major Exams | SPC | 2016-09-26 | Major Exams Coordination | SPC | W1/FS | W17/SS |  |  |  |  | W2/FS | W2/SS | FUC | IN PROGRESS
108 | Operational plans of EE Department Committees 2016\2017: SDC | Enhancing student’ skills through training, Labs and workshops. | SDC | 2016-09-26 | Workshop on “Technical report writing” | SDC | W5/ FS | W6/ FS |  |  |  | • The workshop should contain not only the way or writing but also the plagiarism an ethical issue. Providing the HOD with a report about the activity • Maximum 30% in each work | W6/FS | W7/FS | FUC
109 | Operational plans of EE Department Committees 2016\2017: SDC | Initiate a half year event for exhibition of Senior Design with presentations. | SDC | 2016-09-26 | Workshop “Understanding the senior design process” | SDC | W3/SS | W4/SS |  |  |  | The title can be discussed with the HOD | W4/SS | W5/SS | FUC
110 | Operational plans of EE Department Committees 2016\2017: SDC | Implementation of programs for entrepreneurship and student innovation projects | SDC | 2016-09-26 | Encouraging supervisors to propose innovated project | SDC | W1/FS | W1/SS |  |  |  | Preparing a report about the innovated proposed projects and the way to support and implemented. The material and funded aspects should be included. | W2/FS | W2/SS | FUC
111 | Operational plans of EE Department Committees 2016\2017: SDC | Implementation of programs for entrepreneurship and student innovation projects | SDC | 2016-09-26 | Participating in the college and university best innovation project competition | SDC | W4/FS | W4/SS |  |  |  | Make announcement to all supervisors and instructors to prepare a good report for participation in the computations. | W5/FS | W5/SS | FUC
112 | Operational plans of EE Department Committees 2016\2017: SDC | Implementation of programs for entrepreneurship and student innovation projects | SDC | 2016-09-26 | Discussing the innovated projects and putting a program for implementation | SDC | W16/FS | W17/FS |  |  |  |  | W17/FS | W1/SS | FUC
113 | Operational plans of EE Department Committees 2016\2017: SDC | Enhancing the SDs quality | SDC | 2016-09-26 | Evaluation of CLOs of Senior designs project | SDC | W16/FS | W17/FS |  |  |  |  | W17/FS | W1/SS | FUC
114 | Operational plans of EE Department Committees 2016\2017: SPSC | To make the EE work more flexible and easy to follow | SP&SC | 2016-09-26 | Preparing an EE operational Plans for 2016-2017 | SPSC | W0/FS | W3/FS |  |  |  | The operational plan will be done based on the college strategic plan | W1/FS | W4/FS | FUC | Completed
115 | Operational plans of EE Department Committees 2016\2017: SPSC | To make the EE work more flexible and easy to follow | SP&SC | 2016-09-26 | Providing direction and counsel to the EE department | SPSC | W1/FS | W16/SS |  |  |  |  | W2/FS | W17/FS | FUC | in progress
116 | Operational plans of EE Department Committees 2016\2017: SPSC | Follow-Up the improvement process in the EE departments. | SP&SC | 2016-09-26 | Studying the reedbuck results, analysis and recommendations to make an action plan for improvement purposes. | SPSC | W1/FS | W16/SS |  |  |  | Studying the feedback of units and committees to determine future action plan and responsibilities. | W2/FS | W17/SS | FUC | in progress
117 | Operational plans of EE Department Committees 2016\2017: TQAC | Developing strategies and teaching methods | TQAC | 2016-09-26 | A workshop “Teaching strategies and their effect on the performance of graduates” | TQAC | W1/FS | W4/FS |  |  |  | The title can be discussed with the strategic committee | W2/FS | W5/FS | FUC
118 | Operational plans of EE Department Committees 2016\2017: TQAC | Developing strategies and teaching methods | TQAC | 2016-09-26 | Following and encouraging the progress of using D2L system | TQAC | W0/FS | [5 empty] | W1/FS |  | FUC
119 | Operational plans of EE Department Committees 2016\2017: TQAC | Encourage instructors to attend training on E-learning management system | TQAC | 2016-09-26 | Following and encouraging the progress of using D2L system | TQAC | W0/FS |  |  |  |  | Biannual Report | W1/FS |  | FUC
120
121
122
123
124
125
126
127
128
129
130
131
132

## Development Plan 16-17
Electrical Engineering Department: Development Plan for 2016/2017
Development and Follow-Up
Sr No. | The Document |  |  |  | Action | [6 empty] | Unit Coordinator's Comments | Follow Up |  |  | Remarks
| Title | Recommendation | Proposed by | Date | Activity | Responsibility | Period |  | KPI |  |  |  | Period |  | Responsibility
[7 empty] | From | To | KPI | Target | Actual |  | From | To
1 | Anual Program Report 2015/16 | Stakeholder evaluation | QC | 2016-09-20 | Stakeholder evaluation ratings of the Mission Statement and Objectives | QC | W2 FS |  | Written Analysis Report with recommandation | 100% |  |  | W3 FS |  | FUC | In progress | Starting
2 | Anual Program Report 2015/16 | Stakeholder evaluation | QC | 2016-09-20 | Stakeholder evaluation of the Policy Handbook, including administrative flow chart and job responsibilities | QC | W3 FS |  | Written Analysis Report with recommandation | 100% |  |  | W4 FS |  | FUC | In progress | Completed
3 | Anual Program Report 2015/16 | Students evaluation | QC | 2016-09-20 | Students overall evaluation on the quality of their learning experiences at the institution | QC | W4 FS |  | Written Analysis Report with recommandation | 100% |  |  | W5 FS |  | FUC | In progress | In process
4 | Anual Program Report 2015/16 | Verification of standards of student achievement | QC | 2016-09-20 | independent verification of standards of student achievement | QC | W5 FS |  | Writen verification report | 100% |  |  | W6 FS |  | FUC | In progress | Passed Dead line
5 | Anual Program Report 2015/16 | lab readiness | QC | 2016-09-20 | Preparing the Lab for the classes | Supervisor | 1st week | 2nd week | Lap readiness report | 100% | 100% |  | W2/FS | W3/FS | FUC | Completed
6 | Anual Program Report 2015/16 | Lab Upgrading "if required" | QC | 2016-09-20 | Listing the required lab equipment or components | Supervisor | 1st week | 3nd week | Components list | 100% | 100% |  | W2/FS | W3/FS | FUC | Completed
7 | Anual Program Report 2015/16 | Organizing workshop about research methodology. | QC | 2016-09-20 | Number of faculty members participated in national and international workshops | RCSC | 2016-09-01 | 2017-11-01 | Percentage of faculty members participated in national and international workshops | 100% |  |  | 2016-11-01 | 2016-11-24 | FUC | In progress
8 | Anual Program Report 2015/16 | Organizing workshop How to write research papers. | QC | 2016-09-20 | Guiding the researchers to how to prepare a paper | RCSC | Aug 2016 | June 2017 | Percentage of attended Faculty members | 100% |  |  | Aug 2016 | June 2017 | FUC
9 | Anual Program Report 2015/16 | Offering the assistance for: local (university) and national Scientific Research programs | QC | 2016-09-20 | Giving the assistance to the faculty members to take advantage the different research grants | RCSC | 2016-09-01 | Aug 2017 | Percentage of submitted research proposalsin different programs | 100% |  |  | 2016-09-01 | Aug 2017 | FUC
10 | Anual Program Report 2015/16 | ISI conferences and journals | QC | 2016-09-20 | Offering the updated ISI conferences in the kingdom and in the other gulf countries for 2016-2017 | RCSC | 2016-09-01 | 2017-09-01 | List of ISI conference Percentage of submitted papers and acceptance rate in ISI conference | 100% |  |  | 2016-09-01 | Aug 2017 | FUC
11 | Anual Program Report 2015/16 | Improving the teaching methods in the department | QC | 2016-09-20 | Workshop: How to prepare a lecture | TQAC | W4/FS | W8/FS | Percentage of attended Faculty members and the quality of workshop and discussions | 100% |  |  | W5/FS | W9/FS | FUC | In progress
12 | Anual Program Report 2015/16 | Introducing E-Courses in teaching methods | QC | 2016-09-20 | Following and encouraging the progress of using D2L system (On line conferences and electronic quizzes) | TQAC | W1/FS | W8/FS | Quality and percentage of of the on line conferences and quizzes/course | 100% |  |  | W2/FS | W9/FS | FUC
13 | Anual Program Report 2015/16 | Guide how to prepare a lecture regarding the course description and course objectives | QC | 2016-09-20 | Following and encouraging the progress of using D2L system (On line conferences) | TQAC | W1/FS | W8/FS | Quality of guide | 100% |  |  | W2/FS | W9/FS | FUC
14 | Anual Program Report 2015/16 | Conducting Micro-Project Exhibition | QC | 2016-09-20 | Exhibition | URAC | W4 FS | W6 FS | Participating micro-projects | 100% |  |  | W5/FS | W7/FS | FUC
15 | Anual Program Report 2015/16 | Micro-Projects | QC | 2016-09-20 | Encouraging Faculty to include micro-projects in their courses | URAC | W1 FS | W12 SS | Number of micro-projects | 100% |  |  | W2/FS | W14/SS | FUC
16 | Anual Program Report 2015/16 | Micro-Projects | QC | 2016-09-20 | Review and Recommend extension of micro-projects to Senior Design Level | URAC | W1 FS | W12 SS | Recommended projects | 100% |  |  | W2/FS | W13/SS | FUC
17 | Anual Program Report 2015/16 | Organizing STTP | QC | 2016-09-20 | To organize throughout the semester training programs which will enhance the technical skills of the students on Professional software | URAC | W1 FS | W15 SS | Number of training programs | 100% |  |  | W16/FS | W17/FS | FUC
18 | Anual Program Report 2015/16 | Participation of student micro-projects in Annual Exhibition of Scientific Research and selection of best student micro-projects | QC | 2016-09-20 | Recommending the potential micro-projects to participate in Annual Exhibition | URAC | W2 SS | W12 SS | Percentage of participation | 100% |  |  | W3/SS | W13/FS | FUC
19 | Anual Program Report 2015/16 | Analysis and studying of current curriculum | QC | 2016-09-20 | Making a SWOT analysis for the EE curriculum: Analysis of surveys, course reports and etc... | UPC AEC QC | 12\4\2016 | 20\5\216 | Full SWOT report | 100% | 100% |  | 12\4\2016 | 20\5\216 | FUC | Completed
20 | Anual Program Report 2015/16 | Analysis and studying of current curriculum | QC | 2016-09-20 | Studying the Electrical Engineering trends | UPC | 12\4\2016 | 26\4\2016 | Report | 100% | 100% |  | 12\4\2017 | 20\5\217 | FUC | Completed
21 | Anual Program Report 2015/16 | Analysis and studying of current curriculum | QC | 2016-09-20 | Analyzing the consistency of program vision, mission and objectives with the college | UPC | 15\4\2016 | 22\4\2016 | Report of analysis | 100% | 100% |  | 15\4\2016 | 22\4\2016 | FUC | Completed
22 | Anual Program Report 2015/16 | Analysis and studying of current curriculum | QC | 2016-09-20 | feedback from advisory board regarding current curriculum | program coordinator | 26\4\2016 | 15\5\2016 | Board Advisory report | 100% | 100% |  | 26\4\2016 | 15\5\2016 | FUC | Completed
23 | Anual Program Report 2015/16 | Analysis and studying of current curriculum | QC | 2016-09-20 | Workshop for instructors (1): EE curriculum update requirements | UPC | 20\4\2016 | 27\4\2106 | Attendance percentage | 100% | 100% |  | 20\4\2016 | 27\4\2106 | FUC | Completed
24 | Anual Program Report 2015/16 | Updating the EE curriculum | QC | 2016-09-20 | Updating the SLOs and CLOs | UPC | 15\5\16 | 1\6\16 | Updated and approved SLOs and CLOs | 100% | 100% |  | 15\5\16 | 1\6\16 | FUC | Completed
25 | Anual Program Report 2015/16 | Updating the EE curriculum | QC | 2016-09-20 | Updating courses description: Title, Number, prerequisites, co-requisites, Objectives, contents and textbooks | QC | 15\5\16 | 1\6\16 | Percentage of Updated course description | 100% | 100% |  | 15\5\16 | 1\6\16 | FUC | Completed
26 | Anual Program Report 2015/16 | Updating the EE curriculum | QC | 2016-09-20 | Updating quality issues: teaching strategies, assessment strategies | UPC | 18\9\16 | 18\10\016 | Percentage of Updated quality issues | 100% |  |  | 18\9\16 | 18\10\016 | FUC | In progress
27 | Anual Program Report 2015/16 | Updating the EE curriculum | QC | 2016-09-20 | Workshop for students (2): Updating EE syllabi | UPC | 18\10\16 | 18\11\16 | Attendance percentage | 100% |  |  | 18\10\16 | 18\11\16 | FUC
28 | Anual Program Report 2015/16 | Evaluation of EE updated curriculum | QC | 2016-09-20 | Internal Reviewing | UPC | 18\11\16 | 22\11\16 | Report contents | 100% |  |  | 18\11\16 | 22\11\16 | FUC
29 | Anual Program Report 2015/16 | Evaluation of EE updated curriculum | QC | 2016-09-20 | External reviewing | Program coordinator | 18\11\16 | 18\1\17 | Report contents | 100% |  |  | 18\11\16 | 18\1\17 | FUC
30 | Anual Program Report 2015/16 | Evaluation of EE updated curriculum | QC | 2016-09-20 | Advisory board reviewing | Program coordinator | 18\11\16 | 18\1\17 | Board Advisory report | 100% |  |  | 18\11\16 | 18\1\17 | FUC
31 | Anual Program Report 2015/16 | Evaluation of EE updated curriculum | QC | 2016-09-20 | correction and updating based on the feedback | Program coordinator | 18\11\16 | 18\1\17 | Updated and corrected report | 100% |  |  | 18\11\16 | 18\1\17 | FUC
32 | Anual Program Report 2015/16 | Evaluation of EE updated curriculum | QC | 2016-09-20 | Workshop for instructors (3): Evaluation of EE curriculum | UPC | 18\1\17 | 25\1\17 | Attendance percentage of faculty members | 100% |  |  | 18\1\17 | 25\1\17 | FUC
33 | Anual Program Report 2015/16 | Approval of EE by University council | QC | 2016-09-20 | Preparing documents and evidences | UPC | 25\1\2017 | 2\2\2016 | Prepared documents | 100% |  |  | 27\1\2017 | 4\2\2016 | FUC
34 | Anual Program Report 2015/16 | Approval of EE by University council | QC | 2016-09-20 | Filling the Application form (Approved by University) | UPC | 2\2\2017 | 12\2\2017 | Filled application form | 100% |  |  | 2\2\2017 | 12\2\2017 | FUC
35 | Anual Program Report 2015/17 | Approval of EE by University council | QC | 2016-09-20 | Approval by EE department council | UPC | 2\2\2018 | 12\2\2017 | Approved documents: Council meeting minutes | 100% |  |  | 2\2\2018 | 12\2\2017 | FUC
36 | Anual Program Report 2015/16 | Approval of EE by University council | QC | 2016-09-20 | Approval by CoE council | Program coordinator | 12\2\2017 | 19\2\2017 | Approved documents: Council meeting minutes | 100% |  |  | 12\2\2017 | 19\2\2017 | FUC
37 | Anual Program Report 2015/16 | Approval of EE by University council | QC | 2016-09-20 | sending the vice-rectorate for final approval | Program coordinator | 19\2\2017 | 26\2\2017 | Approved documents: Council meeting minutes | 100% |  |  | 19\2\2017 | 26\2\2017 | FUC
38 | Anual Program Report 2015/16 | Courses Add/drop | QC | 2016-09-20 | Follow-up the add/drop process and schedule conflicts | UCSC | 1st week of each semester | Mid of 2nd week | Number of petitions and conflicts | 100% | 100% |  | W1/FS | W3/SS | FUC | Completed
39 | Anual Program Report 2015/16 | Preparing the next semester schedule | QC | 2016-09-20 | Collect the data about the number of students in each level, track, number of faculty members and preparing the first draft of the timetable | UCSC | 5th week | 8th week | Collected data and Comments from the college committee | 100% |  |  | W6/FS | W7/SS | FUC
40 | Anual Program Report 2015/16 | Seminar for students in level 7 to select their track | QC | 2016-09-20 | Organizing a seminar for students in level 7 to help them to select their track | UCSC | 6th week |  | Make sure that all students in level 7 participate and interact (Attending students) | 100% |  |  | W6/FS | W7/SS | FUC
41 | Anual Program Report 2015/16 | Track registration for the next semester | QC | 2016-09-20 | Completing the tracks registration process for the students of level 7 | UCSC | 6th week | 7th week |  | 100% |  |  | W6/FS | W8/SS | FUC
42 | Anual Program Report 2015/16 | Scientific Visits | QC | 2016-09-20 | Arranging visits for different companies | UCSC | 8th week | 13th week |  | 100% |  |  | W9/FS | W15/SS | FUC
43 | Anual Program Report 2015/16 | Interviews | QC | 2016-09-20 | Arranging exit interview with the senior students | UCSC | 13th week of each semester |  |  | 100% |  |  | W13/FS | W15/SS | FUC
44
45
46
47

## All Units
Unit | Abb | Name | Position
Academic Accreditation Committee | AAC | Dr. Abdullah Almuhaisen | Coordinator
|  | Dr. Abdel-Rahman Al-Qawasmi | Member
|  | Dr. Abdullah Al-Ahmadi | Member
|  | Dr. Praveen | Member
Assessment and Evaluation Committee | AEC | Dr. Muhamed Ouda | Coordinator
|  | Dr. Abdullah Al-Ahmadi | Member
|  | Eng. Mohammad Humran | Member
|  | Eng. Badr Al Harbi | Member
Bridging Program | BP | Dr. Abdel-Rahman Al-Qawasmi | Executive Supervisor
Department Service Committee | DSC | Dr. Yazeed Qasaymeh | Coordinator
|  | Eng. Hussam Habibeh | Member
|  | Eng. Muhammad Humran Khan | Member
Documentation and Archiving Committee | DAC | Eng. Muhammad Humran Khan | Coordinator
|  | Eng. Mohammad Abdul Baseer | Member
Engineering Practice Committee | EPC | Dr. Fathi Kallel | Coordinator
|  | Dr. Ahmed Galal Abo-Khalil | Member
|  | Eng. Faisal Al Harbi | Member
velopment and Follow-Up | GPC | Dr. El Manaa Barhoumi | Coordinator
|  | Dr. Ahmed Galal Abo-Khalil | Member
|  | Dr. Abdel Rahman Al-Qawasmi | Member
Follow Up Committee | FUC | Dr. Fathi Kallel | Coordinator
Interviewing Committee | IC | Dr. Abdullah Almuhaisen | Coordinator
|  | Dr. Abdel Rahman Al-Qawasmi | Member
|  | Dr. Ahmed Galal Abo-Khalil | Member
Lab Developments Committee | LDC | Dr. Muhamad Zubair | Coordinator
|  | Eng. Talha Yazdani | Member
|  | Eng. Mohammad Abdul Baseer | Member
Quality Committee | QC | Dr. Abdullah Al-Ahmadi | Coordinator
|  | Dr. Praveen | Member
|  | Dr. Yazeed Qasaymeh | Member
|  | Eng. Ahamd AlTwejari | Member
Research & Community Services Committee | RCSC | Dr. Youcef Berrouche | Coordinator
|  | Dr. Ahmed Galal Abo-Khalil | Member
|  | Eng. Mohammad Abdul Baseer | Member
|  | Eng. Talha Yazdani | Member
Scheduling Program Committee | SPC | Dr. Ahmed Galal Abo-Khalil | Coordinator
|  | Dr. Abdullah Al-Ahmadi | Member
|  | Eng. Talha Yazdani | Member
Senior Design Committee | SDC | Dr. Ahmad Bilal | Coordinator
Strategic Planning & Steering Committee | SPSC | Dr. Abdullah Almuhaisen | Coordinator
|  | Dr. Abdulrahman Alqawasmi | Member
|  | Dr. Ahamed Abokhalil | Member
Teaching Quality Assurance Committee | TQAC | Dr. Muhamed Ouda | Coordinator
|  | Dr. Praveen | Member
|  | Dr. Muhamad Zubair | Member
|  | Eng. Mohammad Abdul Baseer | Member
Undergraduate Coordination & Support Committee | UCSC | Dr. Ahmed Galal Abo-Khalil | Coordinator
|  | Eng. Mohammad Abdul Baseer | Member
Undergraduate Program Committee | UPC | Dr. Abdel Rahman Al-Qawasmi | Coordinator
|  | Dr. El Manaa Barhoumi | Member
|  | Dr. Ahmed Galal Abo-Khalil | Member
|  | Eng. Muhammad Humran Khan | Member
Undergraduate Research & Assistance Committee | URAC | Dr. Praveen | Coordinator
|  | Dr. Ahmed Galal Abo-Khalil | Member
|  | Dr. Youcef Berrouche | Member
|  | Eng. Talha Yazdani | Member
Web Administration Committee | WAC | Eng. Hussam Habibeh | Coordinator
|  | Eng. Muhammad Humran Khan | Member